## Q4
Week | Fronted | Backend | Continuous Integration | Continuous Delivery
2020-11-20 | Vue.Js - Project setup | Build System | Github Repository
2020-11-27 | Vue.Js - Basic UI | API Set-Up (no data) | Makefile & Scripts
2020-12-04 | Vue.Js - Connect to API | Business Logic Implementation | Local Tests
2020-12-11 | Vue.Js - Build UI for Business Logic |  | GitHub Actions Config
2020-12-18 |  |  | Verify GitHub Actions
2020-12-25 |  |  |  | Set-Up Azure Pipeline
2021-01-01 |  |  | Testing & Bugfixing | Configure Pipeline.yaml
2021-01-08 |  |  | Testing & Bugfixing | Set-Up Locust
2021-01-15
2021-01-22 | Frontend Ready for QA | Backend Ready for QA |  | Testing & Bugfixing
2021-01-29 | Testing & Bugfixing | Testing & Bugfixing |  | Testing & Bugfixing
2021-02-05 | Testing & Bugfixing
| Goals | Goals
| Deployed on Azure | ML API | Automation | WebApp in Azure App Services
| Vue.Js | Logging & Tracing | Testing | Pipeline in Azure DevOps
|  |  | Linting | Load-tested
Scripts